## WILCO Update Status
WILCO App Update Status Checklist
Last reviewed: 2026-05-29 · 32 items total
✅ Built ¦ ⚠️ Partial ¦ ❌ Not Built
# | Feature | Category | Status | Notes
1 | AI Ability to Modify Programming (with Permission) | Core Architecture | Done | Added
2 | % of 1RM Auto-Adjustment Across All Future Sessions | Core Architecture | Testing | Epley 1RM calculated and PRs logged to 'prs' table. Future session targets do not yet auto-recalculate from new max — propagation logic not built. | Need to test further applications
3 | Full Onboarding Question Template | Goal-Based Setup | ⚠️ Partial | Sport, goal, team code, coach info collected at signup. Extended questions (equipment access, injury history, position, training schedule, physical stats) not yet included. | Add to the AI logic to ask for specific goals or targets during it's first chat with an athlete. Then log that into their programming.
4 | Height/Weight/Gender/Age Benchmarks | Goal-Based Setup | ❌ Not Built | No benchmark system exists. Physical stats not collected at signup. Annual age update, monthly height/weight prompts, and relative performance display not built. | Add age, height, weight, and email address to the onboarding process for sign up.
5 | Weekly Digest — Athlete Version (In-App) | Proof Feed | ❌ Not Built | Weekly coach email report mentioned in UI copy but not confirmed end-to-end (May 20 log: 'not yet verified'). Athlete in-app version with trend callouts and next-week focus not built. | Add a weekly email report for the athletes that talks about their progress and steps to focus on. As well as storing them in the progress tab on the app.
6 | Monthly Recap + Reflection Dialogue | Proof Feed | ❌ Not Built | No monthly recap or AI dialogue system exists. Context management (3-month auto-delete, flagged long-term entries) not built. | Add into the AI logic a monthly recap prompt that lists stats and accomplishments, and then asks questions to refine the programming going forward.
7 | Progress Report Tab (Coach Dashboard) | Proof Feed | ❌ Not Built | Coach dashboard exists but no dedicated Progress Report tab. Weekly/monthly digests currently routed to email, not an in-app tab. | Same as above. Just add to the coaches dashboard so they can see it.
8 | Comeback Protocol | AI Coaching Intelligence | DONE | No missed-session detection or comeback plan logic exists. AI does not currently detect or respond to training gaps with a return-to-training plan. | DONE
9 | Plateau Breaker (Intelligent, Not Automatic) | AI Coaching Intelligence | Testing | No plateau detection in Proof Feed. No proactive flagging or coach authorization flow built. | Need more data to determine if it will recognize a plateau.
10 | Proactive AI Trend Notifications (In Proof Feed Only) | AI Coaching Intelligence | Done | No trend analysis (time-of-day performance, sleep impact, consistency patterns) surfaced anywhere. Proof Feed doesn't exist yet. | DONE
11 | Pain-Adaptive Programming (Session Rebuild) | AI Coaching Intelligence | Done | Pain flags parsed from messages, alternatives suggested in chat, resolved_pain synced to Supabase. Full session rebuild (requires program modification system) not built. | Done
12 | Train Anywhere Mode (Time-Bounded Adjustment) | AI Coaching Intelligence | ✅ Built | Fully built (May 28). AI asks about equipment/space/duration, generates temp program saved to temp_program_text, shows gold ✈️ badge in coach dashboard, auto-reverts on 'I'm back' signals. | Done
13 | Quick Log (Session Table on Command) | Logging | ❌ Not Built | No Quick Log button or on-demand session table generation. Logging is done through open chat only. | DENIED!
14 | Workout Streaks | Accountability & Engagement | ❌ Not Built | No streak tracking. No 4-sessions/week threshold logic or streak display built. | Add to the weekly and monthly report. Add an icon to the chat or on the screen.
15 | Team Leaderboard (Monthly Digest — School) | Accountability & Engagement | ❌ Not Built | No leaderboard logic. Monthly digest doesn't exist yet. Most Improved / Most Impressive Lift / Wildcard categories not built. | Add to the coaches report for now. Revisit once we look at DMs.
16 | WILCO Certified Badge | Accountability & Engagement | ❌ Not Built | No certification tracking. 3+ sessions/week for a full off-season threshold and badge display not built. | Similar to workout streaks. Set a standard and provide something tangible for achieving it.
17 | The WILCO Card (Shareable PR Card) | Sharing & Recruiting | ❌ Not Built | No shareable card generator. PRs are tracked internally but no branded social-ready card output exists. | Share to Social Media. Would take a completely new creation.
18 | College Recruiting Document | Sharing & Recruiting | ❌ Not Built | No recruiting document. College intent not collected at onboarding. Formatted metrics export not built. | Have a lifetime document generation that would give a statistical report showing what each athlete has done.
19 | Athlete Profile Page (Shareable Link) | Sharing & Recruiting | ❌ Not Built | No public-facing athlete profile page or shareable link system built. | Have a more custom individual profile with avatars or icons.
20 | Coach Mass Push Notification | Coach Tools (School) | ❌ Not Built | No mass notification system. Coaches can only view athletes individually on the dashboard — no broadcast messaging. | Good idea, need to research how to accomplish this within the app
21 | Coach-to-Athlete Direct Messaging + Athlete-to-Coach Programming Request | Coach Tools (School) | ❌ Not Built | No in-app direct messaging between coach and athlete. Programming change requests not built — no in-app request/authorization flow. | Good idea, need to research how to accomplish this within the app
22 | Add/Remove Coaches from School Account | Coach Tools (School) | Ongoing | No coach management UI for school admin. Coach accounts exist but no add/remove flow without disrupting athlete data. | Create an admin account for each school so they can individually add/remove coaches and athletes.
23 | Monthly Coach Report | Coach Tools (School) | ❌ Not Built | No monthly team summary or forward-looking programming notes. Progress Report tab (which would house this) not built. | Same as athlete one.
24 | AI Personality Customization (School) | Coach Tools (School) | ❌ Not Built | AI voice is fixed as 'Coach Joe Thomas.' No mechanism for school coaches to customize AI language, tone, or mannerisms. | Customize the colors and appearance and logo but can't change the voice, tone, or language too much
25 | Weekly Coach Check-In Infrastructure | Premium Tier | ❌ Not Built | No structured check-in workflow for Will/Joe to review athlete weeks at scale. Premium tier (Elite) exists in UI but no check-in flow built. | Need to look into that much further.
26 | Direct Coach Messaging (Premium) | Premium Tier | ❌ Not Built | No direct messaging with Will/Joe in-app. Elite tier references email (joe.thomas@commandengineering.com) as fallback — not an in-app system. | Need to look into that much further.
27 | Free Trial Implementation (School 30-Day, Individual 7-Day) | Offer Mechanics | ❌ Not Built | No trial logic. Signup goes directly to tier selection with no no-credit-card trial period. | Money back guarantee after 30 days instead of free trial.
28 | Monthly → Annual Self-Serve Upgrade (Individual) | Offer Mechanics | ⚠️ Partial | Annual billing option exists at signup. In-app self-serve switch from monthly to annual post-signup (via Settings) not confirmed built. | Add a way to upgrade within the app. Look into transition between school to individual memberships when they graduate.
29 | Upgrade Moment Prompt at 30 Days | Offer Mechanics | ❌ Not Built | No 30-day trigger or personalized improvement percentage prompt to surface premium upgrade to base-tier athletes. | Denied!
30 | Terms of Service & Liability Waiver (Completion) | Legal & Compliance | ❌ Not Built | ToS and liability waiver not visible in onboarding flow in current codebase. | Review, finalizae and add to onboarding and website.
31 | FERPA Compliance Package | Legal & Compliance | ❌ Not Built | No Data Processing Agreement template or pre-signed FERPA documentation exists. | Research and develop.
32 | Age Verification & Data Privacy Policy (Completion) | Legal & Compliance | ❌ Not Built | No age verification gate (13+ minimum) or student data privacy policy in the current onboarding flow. | Age added to onboarding, and data privacy covered by terms of service.
SUMMARY
| ✅ Built |  | 1 | 3%
| ⚠️ Partial |  | 5 | 16%
| ❌ Not Built |  | 26 | 81%
| Total Items |  | 32 | 100%